## Sheet1
task | start_date | end_date | level_of_effort
Docline | 2023-08-01 | 2023-10-01 | 3
SpineOMatic updated Alma cloud app (includes learning) | 2023-08-01 | 2023-12-31 | 2
reading list for student affordability project | 2023-08-15 | 2024-05-31 | 3
item policy project match to loan rules | 2023-09-20 | 2023-09-25 | 2
EAD exporter app re-enable | 2023-10-01 | 2023-10-07 | 3
LOCKSS update (mostly leveraging LOCKSS support) | 2023-10-01 | 2023-10-15 | 2
RHEL 7 to RHEL 9 | 2023-10-01 | 2024-02-15 | 3
data center migration | 2023-10-01 | 2024-02-15 | 2
learning, especially Ruby on Rails | 2023-10-01 | 2024-06-30 | 3
Read by QxMD - integration with Alma publishing profile | 2023-10-15 | 2023-10-31 | 2
Medical and Vet Clinical OASIS feed into Alma | 2023-11-01 | 2024-01-31 | 3
loan rule Code4Lib article and collaboration with Getty | 2024-02-01 | 2024-02-28 | 2
course archiving | 2024-03-01 | 2024-03-31 | 3
Leganto working group enhancements | 2024-01-01 | 2024-04-30 | 2
open access work from Chris? | 2024-07-01 | 2024-07-31 | 2
ASPace serve static EADs | 2024-02-01 | 2024-05-31 | 3
ASpace new plugin for staff entering alert in PUI | 2024-06-01 | 2024-08-01 | 2
Alma Primo COP Fulfillment Zone | 2024-09-01 | 2025-04-01 | 3