## Sheet1
task | start_date | end_date
Docline | 2023-08-01 | 2023-10-01
SpineOMatic updated Alma cloud app (includes learning) | 2023-08-01 | 2023-12-31
reading list for student affordability project | 2023-08-15 | 2024-05-31
item policy project match to loan rules | 2023-09-20 | 2023-09-25
EAD exporter app re-enable | 2023-10-01 | 2023-10-07
LOCKSS update (mostly leveraging LOCKSS support) | 2023-10-01 | 2023-10-15
RHEL 7 to RHEL 9 | 2023-10-01 | 2024-02-15
data center migration | 2023-10-01 | 2024-02-15
learning, especially Ruby on Rails | 2023-10-01 | 2024-06-30
Read by QxMD - integration with Alma publishing profile | 2023-10-15 | 2023-10-31
Medical and Vet Clinical OASIS feed into Alma | 2023-11-01 | 2024-01-31
loan rule Code4Lib article and collaboration with Getty | 2023-11-01 | 2024-12-31
course archiving | 2024-01-01 | 2024-01-31
Leganto working group enhancements | 2024-01-01 | 2024-04-30
open access work from Chris? | 2024-01-01 | 2024-05-31
ASPace serve static EADs | 2024-02-01 | 2024-05-31
ASpace new plugin for staff entering alert in PUI | 2024-06-01 | 2024-08-01
Alma Primo COP Fulfillment Zone | 2024-09-01 | 2025-04-01