## Sheet1
task | start_date | end_date | level_of_effort
Docline | 2023-08-01 | 2023-12-01 | 3
reading list student affordability - Phase I - process design and reading list creatoin | 2023-08-15 | 2024-12-01 | 3
reading list student affordability - Phase II - testing and citation creation cloud app | 2023-12-01 | 2024-06-30 | 3
Ruby on Rails Udemy | 2024-01-01 | 2024-03-01 | 1
ASpace PUI streamlining | 2024-01-01 | 2024-03-01 | 3
ASpace name change | 2023-12-01 | 2024-01-07 | 1
ELUNA presentation with Martha about reserves workflow enhancement | 2024-03-01 | 2024-05-15 | 2
LOCKSS update (mostly leveraging LOCKSS support) and RHEL 9 upgrade | 2023-11-01 | 2024-02-01 | 1
Medical and Vet Clinical OASIS feed into Alma | 2024-01-01 | 2024-01-15 | 1
RHEL 7 to RHEL 9 for other servers | 2024-01-01 | 2024-02-01 | 2
Leganto working group enhancements | 2024-01-01 | 2024-02-15 | 3
course archiving | 2024-01-15 | 2024-01-30 | 2
loan rule Code4Lib article and collaboration with Getty | 2024-03-15 | 2024-05-41 | 2
Read by QxMD - integration with Alma publishing profile | 2024-04-10 | 2024-06-10 | 2
SpineOMatic updated Alma cloud app (includes learning) | 2024-06-01 | 2024-06-30 | 2