## Sheet1
task | start_date | end_date | level_of_effort
Docline | 2023-08-01 | 2023-10-01 | 3
SpineOMatic updated Alma cloud app (includes learning) | 2024-06-30 | 2024-07-30 | 2
reading list for student affordability project | 2023-08-15 | 2024-05-31 | 3
item policy project match to loan rules | 2023-09-20 | 2023-09-25 | 2
EAD exporter app re-enable | 2023-10-01 | 2023-10-07 | 3
LOCKSS update (mostly leveraging LOCKSS support) | 2023-10-08 | 2023-10-15 | 1
RHEL 7 to RHEL 9 | 2023-11-01 | 2024-02-15 | 2
data center migration | 2023-11-01 | 2024-02-15 | 2
learning, especially Ruby on Rails | 2023-11-15 | 2023-12-01 | 1
Read by QxMD - integration with Alma publishing profile | 2024-04-10 | 2024-06-10 | 2
Medical and Vet Clinical OASIS feed into Alma | 2023-11-01 | 2023-12-30 | 4
loan rule Code4Lib article and collaboration with Getty | 2024-01-15 | 2024-02-28 | 2
course archiving | 2024-01-15 | 2024-01-30 | 2
Leganto working group enhancements | 2024-01-01 | 2024-04-30 | 2
ASPace serve static EADs | 2024-07-01 | 2024-08-01 | 4
ASpace new plugin for staff entering alert in PUI | 2024-08-02 | 2024-08-30 | 2